## 8-Team
Team no. 8
Team leader | Străchinaru Andreea
Scrum Master | Uilăcan Alexandru-Florin
Testers: | Vornicelu Vlad
Bârsan Marius Sebastian
Albescu Anca
Dumitras Valentin
Gherman Andreea-Bianca

## Checklist
Checklist
Tested on | Windows | Android | iOS
Unauthorized user
Log in Test Cases
1. Registration using Google Account. | Fail | Fail | Fail
2. Authentication using "Login" button. | OK | OK | OK
3. Registration using "Registration" button. | OK | OK | OK
4. Authentication with a valid e-mail. | OK | OK | OK
5. Authentication with a valid password. | OK | OK | OK
6. Authentication with invalid credentials. | Fail | Fail | Fail
Authorized user
Header Test Cases
1. Check the display of the logo(Ca$hify). | OK | OK | OK
2. Check the display of the icon with the first letter of the user's name. | OK | OK | OK
3. Check the display of the "Dark and Light", "Language switch" and "Exit" button. | OK | OK | OK
4. Test return to main page using the logo. | OK | OK | OK
5. Test log out using Exit button. | OK | OK | OK
Start page Test Cases
1. Check showing the introduction message at balance section. | OK | OK | OK
2. Test enter value in the balance. | OK | OK | OK
3. Check current date in transaction form. | OK | OK | OK
4. Date change in transaction form. | OK | OK | OK
5.Insert transaction description in Product description | OK | OK | OK
6. Select category name from Product category. | OK | OK | OK
7. Insert transaction amount in value section. | Fail | Fail | Fail
8. Test Input button. | OK | OK | OK
9. Test Clear button. | OK | OK | OK
10. Delete a transaction from the list. | OK | OK | OK
11. View/Delete/Add a transaction from a specific date. | OK | OK | OK
12. Confirm or Cancel deleting a transaction. | Fail | Fail | Fail
13. Check the decrease or increase of the balance after deleting transaction. | OK | OK | OK
14. Insert incomes in expenses section. | Fail | Fail | Fail
15. Use scroll to navigate through the transaction list. | Fail | Fail | Fail
16. Show transaction Summary from January to current month. | OK | Fail | OK
17. Test Reports button. | OK | OK | OK
Reports Page Test Cases
1. Check display of the Main page button. | OK | OK | OK
2. Test the button for changing months. | OK | OK | OK
3. When changing months an Expenses/Incomes changing button is shown. | OK | OK | OK
4. Transactions from current month are shown in Expenses/Incomes list. | OK | OK | OK
5. Graph is for each product category. | OK | OK | OK

## Test Suite
Ca$hify Test Suite
Login
Test Cases Suite
From TC-1 -> TC-6
Header
Test Cases Suite
From TC-7 -> TC-11
Start Page
Test Cases Suite
From TC-12 -> TC-28
Reports Page
Test Cases Suite
From TC- 29 -> TC-33
Adittional Test Cases Suite
From TC-33 -> TC-34

## Test report
Overall status
| Number of tests planned | 34
| Number of tests executed | 34
| Number of tests passed | 24
| Number of tests failed | 10
Conclusion: | Considering the number of failed tests,
the product is not recommended for use.

## TC-1
ID | TC-1 | Target Description: | Register using Google account
Type | Functional |  | Priority: | Medium
Pre-conditions:
1 | User has the link opened in browser https://kapusta-qa-ro.p.goit.global/
2
Steps
Step |  |  | Expected result |  | Pass | Fail | Bug report ID
1 | The user clicks on the "Google" button |  | Another page automaically opens where the user can choose a goolge account to connect in "Cashify" |  | X
2 | The user chooses a Google account to connect in "Cashify" |  | The user is successfully connected in "Cashify" |  |  | X | BR-1
3
4
5
6
7
Executor: |  | Vornicelu Vlad |  | Date: 05.10.2023

## BR-1
ID | BR-1
Reporter: | Vornicelu Vlad | Assignee: | Developer | Status: | To do
Type: | Functional | Severity: | Critical | Priority: | High
Browser: | Google Chrome, Safari | OS: | Windows, Android, iOS | OS version | 10, 13, 15.5
Summary: | User can't register with google account
Description:
When the user is choosing a google account to connect in "Cashify" a 403 status is displayed
Pre-conditions:
1 | The user has the link https://kapusta-qa-ro.p.goit.global/ opened in browser
2
Steps to reproduce:
1 | The user clicks on the "Google" button
2 | The user chooses a Google account to connect in "Cashify"
3
4
Actual result:
1. Another page automaically opens where the user can choose a goolge account to connect in "Cashify"
2. The user recieves a 403 status.
Expected result:
1. Another page automaically opens where the user can choose a goolge account to connect in "Cashify"
2. The user is successfully connected in "Cashify"
Attachments: | https://drive.google.com/file/d/1AO7PhscTt6mHXq0B-I0Dvjnh7qS5WhYJ/view?usp=sharing
Additional info:

## TC-2
ID | TC-2 | Target Description: | Registration using "Registration" button and valid credentials
Type | Functional |  | Priority: | High
Pre-conditions:
1 | User has the link opened in browser https://kapusta-qa-ro.p.goit.global/
2
Steps
Step |  |  | Expected result |  | Pass | Fail | Bug report ID
1 | User inserts "name.name@yahoo.com" in "email" field |  | The email is validated |  | x
2 | User inserts "12345678" in "password" field |  | The password is validated |  | x
3 | User clicks on "Register" button |  | User has acces in "Cashify" web app |  | x
4
5
6
7
Executor: |  | Vornicelu Vlad |  | Date: 05.10.2023

## TC-3
ID | TC-3 | Target Description: | Register using "Registration" button and invalid credentials
Type | Functional |  | Priority: | High
Pre-conditions:
1 | User has the link opened in browser https://kapusta-qa-ro.p.goit.global/
2
Steps
Step |  |  | Expected result |  | Pass | Fail | Bug report ID
1 | User inserts "name.name.yahoo.com" in "email" field |  | Below the "email" field, the text "Invalid email" appears |  | x
2 | User inserts "123456" in "password" field |  | Below the "password" field the text "Min length 7" appears |  | x
3 | User clicks on "Register" button |  | User recives a pop-up with the text "please enter correct data" |  | x
4
5
6
7
Executor: |  | Vornicelu Vlad |  | Date: 05.10.2023

## TC-4
ID | TC-4 | Target Description: | Registration using "Registration" button and invalid email
Type | Functional |  | Priority: | High
Pre-conditions:
1 | User has the link opened in browser https://kapusta-qa-ro.p.goit.global/
2
Steps
Step |  |  | Expected result |  | Pass | Fail | Bug report ID
1 | User inserts "-d@h00.com" in "email" field |  | Below the "email" field, the text "Invalid email" appears |  |  | x | BR-2
2 | User inserts "12345678" in "password" field |  | The password is validated |  | x
3 | User clicks on "Register" button |  | User recives a pop-up with the text "please enter correct data" |  |  | x | BR-2
4
5
6
7
Executor: |  | Vornicelu Vlad |  | Date: 05.10.2023

## BR-2
ID | BR-2
Reporter: | Vornicelu Vlad | Assignee: | Developer | Status: | To do
Type: | Functional | Severity: | Critical | Priority: | High
Browser: | Chrome, Safari | OS: | Windows, Android, iOS | OS version | 10, 13, 15.5
Summary: | User has acces with invalid email
Description: | User can acces "Cashify" with an invalid email and valid password
Pre-conditions:
1 | The user has the link https://kapusta-qa-ro.p.goit.global/ opened in browser
2 | Email cannot start with "-"
Steps to reproduce:
1 | User inserts "-d@h00.com" in "email" field
2 | User inserts "12345678" in "password" field
3 | User clicks on "Register" button
Actual result:
1. The email is validated
2. User has acces in "Cashify"
Expected result:
1. Below the "email" field, the text "Invalid email" appears
2. The password is validated
3. User recives a pop-up with the text "please enter correct data"
Attachments:
Additional info:

## TC-5
ID | TC-5 | Target Description: | Register using valid mail and invalid password
Type | Functional |  | Priority: | High
Pre-conditions:
1 | User has the link opened in browser https://kapusta-qa-ro.p.goit.global/
2
Steps
Step |  |  | Expected result |  | Pass | Fail | Bug report ID
1 | User inserts "name.2@yahoo.com" in "email" field |  | Email is validated |  | x
2 | User inserts "1234567" in "password" field |  | Below the "password" field the text "Min length 7" appears |  |  | x | BR-3
3 | User clicks on "Register" button |  | User recives an error with the text "SORRY, BUT YOUR DATA ISN'T CORRECT. TRY AGAIN" |  | x
4
5
6
7
Executor: |  | Vornicelu Vlad |  | Date: 05.10.2023

## BR-3
ID | BR-3
Reporter: | Vornicelu Vlad | Assignee: | Developer | Status: | To do
Type: | Functional | Severity: | Major | Priority: | High
Browser: | Chrome, Safari | OS: | Windows , Android, iOS | OS version | 10, 13, 15.5
Summary: | Error not displayed under "password" field
Description:
When the password has 7 characters, under the field an error is not displayed.
Pre-conditions:
1 | The user has the link https://kapusta-qa-ro.p.goit.global/ opened in browser
2
Steps to reproduce:
1 | User inserts "name.2@yahoo.com" in "email" field
2 | User inserts "1234567" in "password" field
3 | User clicks on "Register" button
4
Actual result:
1. The email is validated
2. User recives a pop-up with the text "SORRY, BUT YOUR DATA ISN'T CORRECT. TRY AGAIN"
Expected result:
1. Email is validated
2. Below the "password" field the text "Min length 7" appears
3. User recives a pop-up with the text "please enter correct data"
Attachments:
Additional info:

## TC-6
ID | TC-6 | Target Description: | Authentication with Login button and valid credentials.
Type | Functional |  | Priority: | High
Pre-conditions:
1 | User has the link opened in browser https://kapusta-qa-ro.p.goit.global/
2
Steps
Step |  |  | Expected result |  | Pass | Fail | Bug report ID
1 | User inserts "name.2@yahoo.com" in "email" field |  | Email is validated |  | x
2 | User inserts "123456789" in "password" field |  | Password is validated |  | x
3 | User clicks on "Login" button |  | Page is redirected to the account page |  | x
4
5
6
7
Executor: |  | Vornicelu Vlad |  | Date: 05.10.2023

## TC-7
ID | TC-7 | Target Description: | Check the logo display
Type | Functional |  | Priority: | Low
Pre-conditions:
1 | https://kapusta-qa-ro.p.goit.global/ is open in browser.
2
Steps
Step |  |  | Expected result |  | Pass | Fail | Bug report ID
1 | Enter credentials and log in the account. |  | Page is redirected intro the account on the main page. |  | X
2 | Check the display of the Ca$hify logo on the left side of the header. |  | The Ca$hify logo is displayed on the left side of the header. |  | X
3
4
5
6
7
Executor: |  | Vlad Vornicelu |  | Date: | 2023-10-06

## TC-8
ID | TC-8 | Target Description: | Verify display of the icon with the first letter of the user s name.
Type | Functional |  | Priority: | Low
Pre-conditions:
1 | https://kapusta-qa-ro.p.goit.global/ is open in browser.
2
Steps
Step |  |  | Expected result |  | Pass | Fail | Bug report ID
1 | Enter valid credentials to enter the account. |  | Page is redirected into the account on the main page. |  | X
2 | Check the display of the icon with the first letter of the user s name in the right side of the header. |  | The icon is displayed on the right side of the header. |  | X
3
4
5
6
7
Executor: |  | Vlad Vornicelu |  | Date: | 2023-10-06

## TC-9
ID | TC-9 | Target Description: | Display of the "Dark/Light", "Language switch" and "Exit" buttons.
Type | Functional |  | Priority: | Low
Pre-conditions:
1 | https://kapusta-qa-ro.p.goit.global/ is open in browser.
2
Steps
Step |  |  | Expected result |  | Pass | Fail | Bug report ID
1 | Enter valid credentials to enter the account. |  | The account is opened on the main page. |  | X
2 | Check in the header, the display of the "Dark/Light", "Language switch" and "Exit" buttons. |  | The 3 buttons are displayed in the header of the page. |  | X
3
4
5
6
7
Executor: |  | Vlad Vornicelu |  | Date: | 2023-10-06

## TC-10
ID | TC-10 | Target Description: | Return to main page using the logo.
Type | Functional |  | Priority: | Medium
Pre-conditions:
1 | https://kapusta-qa-ro.p.goit.global/ is open in browser.
2 | User is logged in the account.
Steps
Step |  |  | Expected result |  | Pass | Fail | Bug report ID
1 | Click on Reports button. |  | Reports page is opened. |  | X
2 | Click on Ca$hify logo. |  | User is redirected to the main page. |  | X
3
4
5
6
7
Executor: |  | Gherman Andreea |  | Date: | 2023-10-05

## TC-11
ID | TC-11 | Target Description: | Test log out using Exit button.
Type | Functional |  | Priority: | Medium
Pre-conditions:
1 | https://kapusta-qa-ro.p.goit.global/ is open in browser.
2 | User is logged in the account.
Steps
Step |  |  | Expected result |  | Pass | Fail | Bug report ID
1 | Click on Exit button. |  | Message "Do you really want to log out?" is shown asking YES or NO. |  | X
2 | Click on YES. |  | User is logged out. |  | X
3
4
5
6
7
Executor: |  | Gherman Andreea |  | Date: | 2023-10-05

## TC-12
ID | TC - 12 | Target Description: | Display the introduction message on Balance section.
Type | Functional |  | Priority: | Low
Pre-conditions:
1 | Launch the page: https://kapusta-qa-ro.p.goit.global/
2 | Register with valid credentials.
Steps
Step |  |  | Expected result |  | Pass | Fail | Bug report ID
1 | Login to the website |  | At Home page on Balance section this message has to show up, first time when you login, before putting any amount in the value section:"Hello! Pentru a începe, vă rugăm să depuneți soldul curent al contului dumneavoastră! Nu puteți cheltui bani până nu îi aveți :)"
2
Executor: |  | Andreea Gherman |  | Date: 06.10.2023

## TC-13
ID | TC-13 | Target Description: | Check if after entering value the introduction message from Balance dissapears.
Type | Functional |  | Priority: | Medium
Pre-conditions:
1 | To be logged on the page: https://kapusta-qa-ro.p.goit.global/
2 | User is logged in the account.
Steps
Step |  |  | Expected result |  | Pass | Fail | Bug report ID
1 | Enter value in Balance section. |  | Value is entered. |  | X
2 | Click on Input. |  | Value is inputted. |  | X
3 | Check if the message is still shown. |  | The message dissapeared. |  | X
4
5
6
7
Executor: |  | Gherman Andreea |  | Date: | 2023-10-07

## TC-14
ID | TC-14 | Target Description: | Requirements: After logging into account, the current date is shown
Type | Usability |  | Priority: | Low
Pre-conditions:
1 | To be logged on the page: https://kapusta-qa-ro.p.goit.global/
2
Steps
Step |  |  | Expected result |  | Pass | Fail | Bug report ID
1 | We check that the current date is shown |  | The current date is shown on the left side |  | X
2
3
4
5
6
7
Executor: |  | Uilacan Alexandru |  | Date: | 2023-10-05

## TC-15
ID | TC-15 | Target Description: | Complete the fields for transactions
Type | Functional |  | Priority: | Medium
Pre-conditions:
1 | To be logged on the page: https://kapusta-qa-ro.p.goit.global/
2
Steps
Step |  |  | Expected result |  | Pass | Fail | Bug report ID
1 | We click on the date to change it |  | A calendar opens and we can select a random past or actual date |  | X
2 | We fill the "Product description", min 3 characters, max 20 |  | The text remains in the "Product description" field |  | X
3 | We choose the "Product Category" from the drop-down list. |  | The "Product Category" selected remains in the field. |  | X
4 | We enter an amount according with the format: 40.5 |  | The sum remains in the field |  |  | X | BR-4
5 | We enter an amount integer and at least 1. |  | The sum remains in the field |  | X
6 | We Enter "IMPUT" |  | The amount, beside date, product description and category are stored in the list
7
Executor: |  | Uilacan Alexandru |  | Date: | 2023-10-05

## BR-4
ID | BR-4
Reporter: | Uilacan Alexandru | Assignee: | Developer | Status: | New
Type: | Functional | Severity: | Minor | Priority: | Medium
Browser: | Google Chrome, Safari | OS: | Windows, Android, iOS | OS version | 10, 13, 15.5
Summary: | Entering a sum in the field
Description: | The format of the number is an integer with 2 decimal places, but only positive integer numbers are accepted
Pre-conditions:
1 | To be logged on the page: https://kapusta-qa-ro.p.goit.global/
2
Steps to reproduce:
1 | We enter a number with 2 decimal places in the field for the sum
2
3
4
Actual result:
We get the messege: Please match the required format
Expected result:
The sum will be accepted
Attachments:
Additional info:
The requirement should specify the exact format for the number

## TC-16
ID | TC-16 | Target Description: | The user can change the date and add new transactions
Type | Functional |  | Priority: | Medium
Pre-conditions:
1 | To be logged on the page: https://kapusta-qa-ro.p.goit.global/
2
Steps
Step |  |  | Expected result |  | Pass | Fail | Bug report ID
1 | We click on the date to change it |  | The new date is selected |  | X
2 | We complete the fields in "Transaction description", "Product category" and Sum |  | The fields are filled with the information provided. |  | X
3 | We press "IMPUT" |  | The information we provided appear in the list below, and we can now fill with information about another transaction |  | X
4
5
6
7
Executor: |  | Albescu Anca |  | Date: | 2023-10-07

## TC-17
ID | TC - 17 | Target Description: | Insert transaction amount in the values section.
Type | Functional |  | Priority: | Medium
Pre-conditions:
1 | Open https://kapusta-qa-ro.p.goit.global/ in browser.
2 | Login with username and passoword
3 | Add description in "Product description" and choose a option from Products list
Steps
Step |  |  | Expected result |  | Pass | Fail | Bug report ID
1 | Place the mouse on value section |  | A straight line will be displayed on value section
2 | Type a number which is higher then 0 |  | The number displayed there will change from 0 to the number displayed
3 | Click on the Input button |  | The inputed value will appear on the transactions list
Executor: |  | Andreea Gherman |  | Date: 06.10.2023

## TC-18
ID | TC - 18 | Target Description: | Insert a negative transaction amount in the values section.
Type | Functional |  | Priority: | Medium
Pre-conditions:
1 | Open https://kapusta-qa-ro.p.goit.global/ in browser.
2 | Login with username and passoword
3 | Add description in "Product description" and choose a option from Products list
Steps
Step |  |  | Expected result |  | Pass | Fail | Bug report ID
1 | Place the mouse on value section |  | A straight line will be displayed on value section
2 | Type a negative amount in the value section |  | The negative number will be displayd in the value section
3 | Click on the Input button |  | The inputed value will appear on the transactions list |  |  |  | BR-5
Executor: |  | Andreea Gherman |  | Date: 06.10.2023

## BR-5
ID | BR-5
Reporter: | Gherman Andreea | Assignee: | Developer | Status: | New
Type: | Functional | Severity: | Minor | Priority: | Medium
Browser: | Google Chrome, Safari | OS: | Windows, Android, iOS | OS version | 10, 13, 15.5
Summary: | Negative amount in the Value section
Description: | Test what is happening when you type a negative value
Pre-conditions:
1 | To be logged on the page: https://kapusta-qa-ro.p.goit.global/
2
Steps to reproduce:
1 | Add description in "Product description" and choose a option from Products list
2 | Type a negative amount in the value section
3 | Click Input
4
Actual result:
In the Value section this message is displayed " Please match the requested format"
Expected result:
The inputed value will appear on the transactions list
Attachments:
Additional info:

## TC-19
ID | TC-19 | Target Description: | Test "INPUT" button |  |  |  |  | ID | TC-19 | Target Description: | Test Input button
Type | Functional |  | Priority: | Medium |  |  |  | Type | Functional |  | Priority: | Medium
Pre-conditions: | [7 empty] | Pre-conditions:
1 | Launch https://kapusta-qa-ro.p.goit.global/ in browser | [6 empty] | 1 | Launch https://kapusta-qa-ro.p.goit.global/ in browser
2 | Sign In with valid user and password | [6 empty] | 2 | Sign In with valid user and password
3 | Go to "EXPENSES" tab | [6 empty] | 3. | Go to "INCOME" tab
Steps | [7 empty] | Steps
Step |  |  | Expected result |  | Pass | Fail | Bug report ID | Step |  |  | Expected result |  | Pass | Fail | Bug report ID
1 | Fill in the "Product description" field |  | The written text appears in the field |  |  |  |  | 1 | Click on "Income" button |  | The Income list appears
2 | Select "Transport" from "Product category" list |  | "Transport" is in the "Product category" field |  |  |  |  | 2 | Enter text key to fill out the "Product description" field |  | The text key appears in the field
3 | Enter a positive number greater than 0 in the field |  | The number appears in the field |  |  |  |  | 3 | Select "Salary" from "Product category" list |  | "Salary" is in the "Product category" field
4 | Click "Input" button |  | The transaction will appear in the Expenses list |  |  |  |  | 4 | Enter positive numeric key to fill out the Form Transaction field |  | The numeric key appears in the field
Executor: |  | Albescu Anca |  | Date: 05.10.2023 |  |  |  | 5 | Click on "Input" button |  | The transaction will appear in the Income list
[8 empty] | Executor: |  | Albescu Anca |  | Date: 05.10.2023

## TC-20
ID | TC-20 | Target Description: | Test Clear button Expenses tab |  |  |  |  | ID | TC-20 | Target Description: | Test Clear button Income tab
Type | Functional |  | Priority: | Medium |  |  |  | Type | Functional |  | Priority: | Medium
Pre-conditions: | [7 empty] | Pre-conditions:
1 | Launch https://kapusta-qa-ro.p.goit.global/ in browser | [6 empty] | 1 | Launch https://kapusta-qa-ro.p.goit.global/ in browser
2 | Sign In with valid user and password | [6 empty] | 2 | Sign In with valid user and password
Steps | [7 empty] | Steps
Step |  |  | Expected result |  | Pass | Fail | Bug report ID | Step |  |  | Expected result |  | Pass | Fail | Bug report ID
1 | Enter text key to fill out the "Product description" field |  | The text key appears in the field |  |  |  |  | 1 | Click Income button |  | The Income list appears
2 | Select "Transport" from "Product category" list |  | "Transport" is selected in the "Product category" field |  |  |  |  | 2 | Enter text key in the "Product description" field |  | The text key appear in the "Product description" field
3 | Enter positive numeric key to fill out the Form Transaction field |  | The numeric key appears in the field |  |  |  |  | 3 | Select "Salary" from "Product category" list |  | "Salary" is select from "Product category" field
4 | Click "Clear" button |  | The text key, numeric key and "Transport" will be deleted from the fields |  |  |  |  | 4 | Enter positive numeric key to fill out the Form Transaction field |  | The numeric key appear in the Form transaction
Executor: |  | Albescu Anca |  | Date: 05.10.2023 |  |  |  | 5 | Click "Clear" button |  | The text key, numeric key and "Salary" will be deleted from the fields
[8 empty] | Executor: |  | Albescu Anca |  | Date: 05.10.2023

## TC-21
ID | TC-21 | Target Description: | Delete a transaction from the list Expenses tab |  |  |  |  | ID | TC-21 | Target Description: | Delete a transaction from the list Income tab
Type | Functional |  | Priority: | Medium |  |  |  | Type | Functional |  | Priority: | Medium
Pre-conditions: | [7 empty] | Pre-conditions:
1 | Launch https://kapusta-qa-ro.p.goit.global/ in browser | [6 empty] | 1 | Launch https://kapusta-qa-ro.p.goit.global/ in browser
2 | Sign In with valid user and password | [6 empty] | 2 | Sign in with a valid user and password
Steps | [7 empty] | Steps
Step |  |  | Expected result |  | Pass | Fail | Bug report ID | Step |  |  | Expected result |  | Pass | Fail | Bug report ID
1 | Enter text key to fill out the "Product description" field |  | The text key appear in the "Product Description" field |  |  |  |  | 1 | Click "Income" button |  | The Income list will appear
2 | Select "Transport" from "Product Category" list |  | "Transport" appear in the "Product category" field |  |  |  |  | 2 | Enter text key to fill out the "Product description" field |  | The text key appear in the "Product description" field
3 | Enter positive numeric key to fill out the Form Transaction field |  | The positive numeric key appear in the Form Transaction field |  |  |  |  | 3 | Select "Salary" from "Product category" list |  | "Salary" is select in "Product Category" list
4 | Click "Input" button |  | The transaction appears in the transaction list |  |  |  |  | 4 | Enter positive numeric key to fill out the Form Transaction field |  | The numeric key appear in the Form Transaction field
5 | Click the delete button |  | The transaction will be deleted |  |  |  |  | 5 | Click "Input" button |  | The transaction appear in the transaction list
Executor: |  | Albescu Anca |  | Date: 05.10.2023 |  |  |  | 6 | Click the delete button |  | The transaction will be deleted
[8 empty] | Executor: |  | Albescu Anca |  | Date: 05.10.2023

## TC-22
ID | TC-22 | Target Description: | The User can change the date, view transaction and delete transaction for the selected date
Type | Functional |  | Priority: | Medium
Pre-conditions:
1 | To be logged on the page: https://kapusta-qa-ro.p.goit.global/
2
Steps
Step |  |  | Expected result |  | Pass | Fail | Bug report ID
1 | We try to change in Expenses/Income mode. |  | The date we choose remains selected in Expenses/Income sections |  | X
2 | We selecte dates with transaction of input/output |  | In the section with transaction appear the transactions for the selected date. |  | X
3 | We press the recycle bin icon for transactions in the Expenses/Income sections. |  | After pressing the recycle bin icon the transactions are deleted |  | X
4 | We choose a date and add transactions in Expenses/Income section, with Description, Catergory and Sum |  | The data we entered is stored in the list of transactions |  | X
5
6
7
Executor: |  | Uilacan Alexandru |  | Date: | 2023-10-05

## TC-23
ID | TC-23 | Target Description: | Confirm Deleting transaction |  |  |  |  | ID | TC-23 | Target Description: | Cancel deleting transaction
Type | Functional |  | Priority: | Medium |  |  |  | Type | Functional |  | Priority: | Medium
Pre-conditions: | [7 empty] | Pre-conditions:
1 | Launch https://kapusta-qa-ro.p.goit.global/ in browser | [6 empty] | 1 | Launch https://kapusta-qa-ro.p.goit.global/ in browser
2 | Sign in with a valid user and password | [6 empty] | 2 | Sign in with a valid user and password
3. | Expenses tab is open. | [7 empty] | Income tab is open.
Steps | [7 empty] | Steps
Step |  |  | Expected result |  | Pass | Fail | Bug report ID | Step |  |  | Expected result |  | Pass | Fail | Bug report ID
1 | Enter text key to fill out the "Product description" field |  | The text key appear in the "Product description" field |  |  |  |  | 1 | Enter text key to fill out the "Product description" field |  | The text key appear in the "Product description" field
2 | Select "Transport" from "Product category" list |  | "Transport" is select in "Product category" list |  |  |  |  | 2 | Select "Transport" from "Product category" list |  | "Transport" is select in "Product category" list
3 | Enter positive numeric key to fill out the Form Transaction field |  | The numeric key appear in the Form Transaction field |  |  |  |  | 3 | Enter positive numeric key to fill out the Form Transaction field |  | The numeric key appear in the Form Transaction field
4 | Click "Input" button |  | The transaction appear in the expenses transaction list |  |  |  |  | 4 | Click "Input" button |  | The transaction appear in the expenses transaction list
5 | Click the delete button |  | A pop up message is shown |  |  |  | BR-6 | 5 | Click the delete button |  | A pop up message is shown |  |  |  | BR-6
Executor: |  | Albescu Anca |  | Date: 05.10.2023 |  |  |  | Executor: |  | Albescu Anca |  | Date: 05.10.2023

## BR-6
ID | BR-6 |  |  |  |  | ID | BR-6
Reporter: | Albescu Anca | Assignee: | Developer | Status: | In process | Reporter: | Albescu Anca | Assignee: | Developer | Status: | In process
Type: | Functional | Severity: | Minor | Priority: | Medium | Type: | Functional | Severity: | Minor | Priority: | Medium
Browser: | Firefox, Google Chrome, Safari | OS: | Windows, Android, iOS | OS version | 10, 13, 15.5 | Browser: | Firefox, Google Cgrome, Safari | OS: | Windows, Android, iOS | OS version | 10, 13, 15.5
Summary: | Confirm deleting transaction |  |  |  |  | Summary: | Cancel deleting transaction
Description: | [5 empty] | Description:
| Verify that after click on delete a transaction a pop-up message is shown asking to confirm on cancel the action. | [5 empty] | Verify that after click on delete a transaction a pop-up message is shown asking to confirm on cancel the action.
Pre-conditions: | [5 empty] | Pre-conditions:
1 | Launch https://kapusta-qa-ro.p.goit.global/ in browser |  |  |  |  | 1 | Launch https://kapusta-qa-ro.p.goit.global/ in browser
2 | Sign in with a valid user and password |  |  |  |  | 2 | Sign in with a valid user and password
3. | Expenses tab is open. |  |  |  |  | 3. | Income tab is open
Steps to reproduce: | [5 empty] | Steps to reproduce:
1 | Enter text key to fill out the "Product description" field |  |  |  |  | 1 | Enter text key to fill out the "Product description" field
2 | Select "Transport" from "Product category" list |  |  |  |  | 2 | Select "Transport" from "Product category" list
3 | "Enter positive numeric key to fill out the Form Transaction field" |  |  |  |  | 3 | "Enter positive numeric key to fill out the Form Transaction field"
4 | Click "Input" button |  |  |  |  | 4 | Click "Input" button
5 | Click the delete button |  |  |  |  | 5 | Click the delete button
6 | [5 empty] | 6
Actual result: the pop-up message doesn-t show | [5 empty] | Actual result: the pop-up message doesn-t show
Expected result: a pop-up message is shown asking to confirm the action. | [5 empty] | Expected result: a pop-up message is shown asking to confirm the action.

## TC-24
ID | TC-24 | Target Description: | Testare "Titlul părții teoretice"
Type | Functional |  | Priority: | Medium
Pre-conditions:
1 | To be logged on the page: https://kapusta-qa-ro.p.goit.global/
2
Steps
Step |  |  | Expected result |  | Pass | Fail | Bug report ID
1 | In the Income section we select a date and imput a sum of money (description, catery, sum) |  | In the "Sumarry" section on the right, the sum of money from the month we selected the date increases with the sum we entered |  | X
2 | In the Expensest section we select a date and imput a sum of money (description, catery, sum |  | In the "Sumarry" section on the right, the sum of money from the month we selected the date decreases with the sum we entered |  | X
3 | In the Income section we select a date and imput a sum of money (description, catery, sum) |  | The "Balance" increases with the sum we entered |  | X
4 | In the Expenses section we select a date and imput a sum of money (description, catery, sum) |  | The "Balance" decreases with the sum we entered |  | X
5
6
7
Executor: |  | Uilacan Alexandru |  | Date: | 2023-10-05

## TC-25
ID | TC-25 | Target Description: | Use scroll to navigate through the transaction list.
Type | Functional |  | Priority: | Medium
Pre-conditions:
1 | https://kapusta-qa-ro.p.goit.global/ is open in browser.
2 | User is logged in the account.
3.
Steps
Step |  |  | Expected result |  | Pass | Fail | Bug report ID
1 | User makes 12 transactions. |  | 12 transactions are shown in the list. |  | X
2 | User uses scroll to navigate and find an specific transaction. |  | User navigates through the list. |  |  | X | BR-7
3
4
5
6
7
Executor: |  | Dumitras Valentin |  | Date: | 2023-10-05

## BR-7
ID | BR-7
Reporter: | Dumitras Valentin | Assignee: | Developer | Status: | New
Type: | Functional | Severity: | Major | Priority: | Medium
Browser: | Google Chrome, Safari | OS: | Windows,Android, iOS | OS version | 10, 13, 15.5
Summary: | Use scroll to navigate through the transaction list.
Description: | When the transaction list is full, the user can use scroll to navigate through the list.
Pre-conditions:
1 | https://kapusta-qa-ro.p.goit.global/ | is open in browser.
2 | The user in logged in the account.
Steps to reproduce:
1 | User makes 12 transactions to fill the list.
2 | 12 transactions are shown.
3 | User uses scroll to navigate through the list.
4
Actual result:
Scroll is not functioning, the list doesn t scroll.
Expected result:
The scroll functions and navigates through the list.
Attachments:
Additional info:

## TC-26
ID | TC-26 | Target Description: | Transaction Summary is shown from January to current month.
Type | Functional |  | Priority: | Medium
Pre-conditions:
1 | https://kapusta-qa-ro.p.goit.global/ is open in browser.
2 | User is logged in the account.
Steps
Step |  |  | Expected result |  | Pass | Fail | Bug report ID
1 | Check for Summary table on Expenses and Incomes. |  | Summary table is shown on the main page of the account. |  | X | X | BR-8
2 | Check in the Summary table at Expenses if the values and the months from January to October are shown. |  | Values and months from January to October are shown in Expenses Summary. |  | X | X | BR-8
3 | Check in Summary table Incomes if values and months from January to October are shown. |  | Values and months are shown in Income Summary. |  | X | X | BR-8
4
5
6
7
Executor: |  | Dumitras Valentin |  | Date: | 2023-10-05

## BR-8
ID | BR-8
Reporter: | Dumitras Valentin | Assignee: | Developer | Status: | New
Type: | Functional | Severity: | Major | Priority: | High
Browser: | Google Chrome | OS: | Android | OS version | 13
Summary: | Transaction Summary is shown from January to current month.
Description: | In both Incomes and Expenses the Summary is shown containing values and months from January to October.
Pre-conditions:
1 | https://kapusta-qa-ro.p.goit.global/ |  | is open in browser
2 | The user is logged in the account.
Steps to reproduce:
1 | Check for the Summary on the Expenses section.
2 | Check for the Summary on the Income section.
3
4
Actual result:
The Summary is not shown.
Expected result:
The Summary is shown on both Expenses and Income.
Attachments:
Additional info:

## TC-27
ID | TC-27 | Target Description: | Verify that when click on Reports button the Reports page opens.
Type | Functional |  | Priority: | Medium
Pre-conditions:
1 | Cashify is opened in the browser
2 | The user is logged in
Steps
Step |  |  | Expected result |  | Pass | Fail | Bug report ID
1 | Press on the Reports button in the top right corner |  | The Reports page opens |  | Passed
2
3
Executor: |  | Barsan Marius Sebastian |  | Date: 05.10.2023

## TC-28
ID | TC-28 | Target Description: | Verify if the Main page button is shown.
Type | Functional |  | Priority: | Medium
Pre-conditions:
1 | Cashify is opened in the browser
2 | The user is logged in
Steps
Step |  |  | Expected result |  | Pass | Fail | Bug report ID
1 | Press on the Reports button in the top right corner |  | The Reports page opens |  | Passed
2 | Verify if the Main page button is shown. |  | The main page button is in the top left corner of the page |  | Passed
3 | Press on the Main page button |  | The user is redirected to the main page |  | Passed
Executor: |  | Barsan Marius Sebastian |  | Date: 05.10.2023

## TC-29
ID | TC-29 | Target Description: | Check if the button for changing from the current month to the previous ones is shown and functional.
Type | Functional |  | Priority: | High
Pre-conditions:
1 | Cashify is opened in the browser
2 | The user is logged in
Steps
Step |  |  | Expected result |  | Pass | Fail | Bug report ID
1 | Press on the Reports button in the top right corner |  | The Reports page opens |  | Passed
2 | Verify if the Current Period is shown |  | The Current Period text is shown in the top right corner |  | Passed
3 | Verify if the user can change the months by pressing the left and right arrows |  | The user can successifuly change the Current Period month |  | Passed
Executor: |  | Barsan Marius Sebastian |  | Date: 05.10.2023

## TC-30
ID | TC-30 | Target Description: | Verify that after changing the month an Expenses/Incomes changing button is shown.
Type | Functional |  | Priority: | High
Pre-conditions:
1 | Cashify is opened in the browser
2 | The user is logged in
Steps
Step |  |  | Expected result |  | Pass | Fail | Bug report ID
1 | Press on the Reports button in the top right corner |  | The Reports page opens |  | Passed
2 | Press on the Current Period arrows to change the month |  | The month changes |  | Passed
3 | Verify that after changing the month an Expenses/Incomes changing button is shown. |  | The Expenses/Income button is shown in the center of the screen |  | Passed
Executor: |  | Barsan Marius Sebastian |  | Date: 05.10.2023

## TC-31
ID | TC-31 | Target Description: | Transactions from current month are shown in Expenses/Incomes list.
Type | Functional |  | Priority: | High
Pre-conditions:
1 | Cashify is opened in the browser
2 | The user is logged in
Steps
Step |  |  | Expected result |  | Pass | Fail | Bug report ID
1 | Press on the Reports button in the top right corner |  | The Reports page opens |  | Passed
2 | Verify the Expenses/Income tab on the current month |  | The Expenses/Income tab show the current month expenses and income |  | Passed
Executor: |  | Barsan Marius Sebastian |  | Date: 05.10.2023

## TC-32
ID | TC-32 | Target Description: | Verify if a graph is shown for each product category
Type | Functional |  | Priority: | High
Pre-conditions:
1 | Cashify is opened in the browser
2 | The user is logged in
Steps
Step |  |  | Expected result |  | Pass | Fail | Bug report ID
1 | Press on the Reports button in the top right corner |  | The Reports page opens |  | Passed
2 | Verify the Expenses/Income tab on the current month have graphs for each category |  | The Expenses/Income tab show a graph for each category |  | Passed
Executor: |  | Barsan Marius Sebastian |  | Date: 05.10.2023

## TC-33
ID | TC-33 | Target Description: | Webpage freezes after a time of inactivity
Type | Functional |  | Priority: | Medium
Pre-conditions:
1 | To be logged on the page: https://kapusta-qa-ro.p.goit.global/
2
Steps
Step |  |  | Expected result |  | Pass | Fail | Bug report ID
1 | We imput a sum in Balance field |  | The Balance increases with the sum |  | X
2 | We add expenses and incomes |  | The balance increases and decreases with the sums, accordingly |  | X
3 | We leave the site and user other tabs, then after ~10 minutes we came back |  | The site is ready for our imput |  |  | X | BR-9
4
5
6
7
Executor: |  | Uilacan Alexandru |  | Date: | 2023-10-07

## BR-9
ID | BR-9
Reporter: | Uilacan Alexandru | Assignee: | Developer | Status: | New
Type: | Functional | Severity: | Major | Priority: | High
Browser: | Google Chrome, Safari | OS: | Windows, Android, iOS | OS version | 10, 13, 15.5
Summary: | Webpage freezes after a time of inactivity
Description: | After working in the app for a time, if time passes without activity,
the program will freeze when trying to resume work.
Pre-conditions:
1 | To be logged on the page: https://kapusta-qa-ro.p.goit.global/
2
Steps to reproduce:
1 | We work in the app, adding expenses and incomes.
2 | We leave the app, working on other apps, or leaving the PC
3 | We try to resume work on the app
4
Actual result:
3 orange point blink without the app to respond.
Expected result:
The app is ready to resume work
Attachments:
Additional info:

## TC-34
ID | TC-34 | Target Description: | Test the effect of pressing F5
Type | Functional |  | Priority: | Medium
Pre-conditions:
1 | To be logged on the page: https://kapusta-qa-ro.p.goit.global/
2
Steps
Step |  |  | Expected result |  | Pass | Fail | Bug report ID
1 | Press F5 to refresh the page. |  | The page refreshes. |  |  | X | BR-10
2
3
4
5
6
7
Executor: |  | Uilacan Alexandru |  | Date: | 2023-10-07

## BR-10
ID | BR-10
Reporter: | Uilacan Alexandru | Assignee: | Developer | Status: | New
Type: | Functional | Severity: | Major | Priority: | High
Browser: | Google Chrome, Safari | OS: | Windows, Android, iOS | OS version | 10, 13, 15.5
Summary: | Test the effect of pressing F5
Description: | When pressing F5 to refresh the page, the site crashes.
Pre-conditions:
1 | To be logged on the page: https://kapusta-qa-ro.p.goit.global/
2
Steps to reproduce:
1 | We press F5 to refresh the page
2
3
4
Actual result:
We get an error message: "The requested URL was not found on the server"
Expected result:
The pages refreshes.
Attachments:
Additional info: